## GanttChart
Summer Institute Project
| Program Lead: |  | TBD
| Project Start Date: |  | 2019-06-10 | time axis 2019-06-10 to 2019-07-28
| Display Week: |  | 1 |  |  |  |  | 2019-06-10: Week 1; 2019-06-17: Week 2; 2019-06-24: Week 3; 2019-07-01: Week 4; 2019-07-08: Week 5; 2019-07-15: Week 6; 2019-07-22: Week 7
| Plan Developed by: |  | Enter PM Name Here |  |  |  |  | 2019-06-10: 2019-06-10; 2019-06-17: 2019-06-17; 2019-06-24: 2019-06-24; 2019-07-01: 2019-07-01; 2019-07-08: 2019-07-08; 2019-07-15: 2019-07-15; 2019-07-22: 2019-07-22
WBS | Task | Lead/Task Manager | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Data collection and analysis
1.1 | Identify relevant CZOs and data repository | Brittany | 2019-06-21 | 2019-06-22 | 2 | 50% | 1
1.2 | Download data and start representing data in R (time-series, simple statistic graphs, signatures...) Is there anything interesting / strange? Should we reconsider? | Brittany, Stefany, Ishrat | 2019-06-22 | 2019-06-26 | 5 | 0% | 3
1.3 | ArcGIS/QGIS: identify data with spatial properties, convert in appropriate format (raster, vector) for using in models | Brittany, Federico | 2019-06-24 | 2019-06-26 | 3 | 0% | 3
1.4 | FIltering input data: decide time window(s) of data to use as input, at least for first attempts (calibration) Isolate different events to simulate, possibly in different seasons, different durations, magnitude | All | 2019-06-26 | 2019-06-27 | 2 | 0% | 2
1.5 | [Insert Rows above this one, then Hide or Delete this row]
2 | Literature review
2.1 | Learn about, study code of existing models (how many do we need?) |  | 2019-06-20 | 2019-06-26 | 7 | 10% | 5
2.1.1 | HBV, SBM (suggested by Hilary) | Federico | 2019-06-20 | 2019-06-26 | 7 | 40% | 5
2.1.2 | Sacramento (suggested by Hilary) | Stefany | 2019-06-20 | 2019-06-26 | 7 | 10% | 5
2.1.3 | VIC (suggested by Hilary) | Ishrat | 2019-06-20 | 2019-06-26 | 7 | 10% | 5
2.2 | Science-based formulations of infiltration and saturation excess processes (how many do we need) | Federico, Ishrat, Stefany | 2019-06-26 | 2019-06-28 | 3 | 10%
2.2.1 | TOPMODEL (from Gao, see Bevin) | Stefany | 2019-06-26 | 2019-06-28 | 3 | 10%
2.2.2 | HSC-MCT (from Gao, see …) | Ishrat | 2019-06-26 | 2019-06-28 | 3 | 10%
2.2.3 | Our own, least number of parameters | Federico | 2019-06-26 | 2019-06-28 | 3 | 10%
2.3 |  |  |  | 0 |  | 0% | 0
2.4 | [Insert Rows above this one, then Hide or Delete this row] |  |  |  | 10
3 | Modeling: Clear Creek, IA
3.1 | Modify and/or create code to model formulations | All (?) | 2019-06-28 | 2019-07-07 | 10 | 0% | 6
3.2 | Run NWM | Ishrat (?) | 2019-06-28 | 2019-07-07 | 10 | 0% | 6
3.3 | Start running our models and code | All (?) | 2019-07-02 | 2019-07-07 | 6 | 0% | 4
3.4 | Run, check, revise, fix; repeat | All (?) | 2019-07-02 | 2019-07-07 | 6 | 0% | 4
3.5 |  |  |  | 0 |  | 0% | 0
3.6 | [Insert Rows above this one, then Hide or Delete this row]
4 | Model application: larger Iowa, Arizona
4.1 | Prepare data for larger study areas | Brittany | 2019-07-01 | 2019-07-07 | 7 | 0% | 5
4.2 | Run, check, revise, fix; repeat | All | 2019-07-08 | 2019-07-14 | 7 | 0% | 5
4.3 |  |  |  | 1900-01-05 | 7 | 0% | 0
4.4 |  |  |  | 0 |  | 0% | 0
4.5 | [Insert Rows above this one, then Hide or Delete this row]
5 | Analysis of results and revise models
5.1 | Connect with other scaling and hydroinformatics groups | All | 2019-07-01 | 2019-07-15 | 15 | 0% | 11
5.2 | Discuss results, highlight problems (try to fix) | All | 2019-07-08 | 2019-07-20 | 13 | 0% | 10
5.3 |  |  |  | 0 |  | 0% | 0
5.4 |  |  |  | 0 |  | 0% | 0
6 | Writing
6.1 | Take notes, share on Drive/github | All | 2019-06-20 | 2019-07-24 | 35 | 0% | 25
6.2 | Write a paragraph every day of salient things we did | All | 2019-06-24 | 2019-07-18 | 25 | 0% | 19
6.3 | Reorganize written parts | Brittany | 2019-07-08 | 2019-07-20 | 13 | 0% | 10
6.4 | Finalize paper and presentation | All, Brittany leads | 2019-07-21 | 2019-07-24 | 4 | 0% | 3
6.5 | [Insert Rows above this one, then Hide or Delete this row]
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to control the numbering, but the formulas are different for different levels.
Note on B7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.